## Healthcare
Goal # | Objective- Strategy | Member Assigned | Due Date | Completed
1 | 1.1.1 Advocate for Policy Change - pamphlet for hospitals to encourage recruitment and retention of ASL certified interpreters. |  | 2020-05-13
| 1.1.4 Outreach and Educate - develop educational materials to increase sensititity and understanding about target population's access and rights. |  | 2020-05-13
| 1.1.2 Collaborative Training Efforts - Partner with hospitals, advocacy organizations and medical board to offer training for medical providers. |  | 2021-07-01
| 1.1.3 Enhance Education Efforts - Partner with Medical Schools to incorporate education and information re: the target population in curriculm. |  | 2021-07-01
Activity Updates
2019-11-13 | Workgroup established - Jeff Beardsley, Catherine Neilsen (potentially once appointed.)

## Outreach
Goal # | Objective- Strategy | Member Assigned | Due Date | Completed
1 | 1.2.2 Develop a Plan - outreach and training to mental health providers to increase awareness and understanding of culture and rights of the target population. |  | 2020-03-19
3 | 3.2.2 Coordinate Training Opportunities with Deaf Centers of NV and other stakeholders to conduct workshops and townhalls for the target population. |  | 2020-03-19
3 | 3.3.1 Collaborative Training Efforts - partner with NDALC to provide training to the target population about the ADA and how to advocate for themselves. |  | 2020-05-13
4 | 4.2.1 Research and Identify - best practice framework to offer family to family and peer mentors. |  | 2020-07-08
1 | 1.4.4 Outreach and Educate - outreach to NV businesses to introduce communication access options. |  | 2021-07-01
3 | 3.3.2 Outreach and Educate - develop and disseminate materials that educate the target population about their rights, including the legislative process. |  | 2021-07-01
4 | 4.2.2 Support Implementation Efforts - support communtiy based partner efforts to implement family to family and peer mentor services. |  | 2021-07-01
4 | 4.2.3 Cross Coordination - work with communtiy partners to support cross-coordination with other family service organizations. |  | 2021-07-01
Activity Updates
2019-11-13 | Workgroup established - Jeff Beardsley ,Maureen Fradianni and Susan Beckett
2019-11-13 | Need support from Director for mailing addresses.
2019-11-13 | Working on plan for a Pahrump townhall meeting.

## Education
Goal # | Objective- Strategy | Member Assigned | Due Date | Completed
1 | 1.3.2 Advocate for a Consistent Approach - work with DOE to create and utilize a standard/universal communication plan |  | 2020-03-19
1 | 1.3.1 Advocate for Policy Change - develop a policy recommendation to the DOE to incorporate Certified Education Interpreters as a standard component of the education system. |  | 2020-07-08
1 | 1.3.3 Advocate for Enhanced Services - work with DOE and other interested parties to support availability of transition specialists throughout districts. |  | 2021-07-01
1 | 1.3.4 Advocate for Policy Change - work with Voc Rehab to identfity best practices in providing transitional supports to students. |  | 2021-07-01
Activity Updates
2019-11-13 | Workgroup established - Maureen Fradianni, Eric Wilcox, and Diana Loeffler
2019-11-13 | Letter with the approved Communication Plan will be sent to Will Jensen.

## Employment
Goal # | Objective- Strategy | Member Assigned | Due Date | Completed
1 | 1.4.1 Workforce Development - Advocate with state Human Resources to support 5% pay enhancement for state employees who are ASL profiecient. |  | 2021-07-01
1 | 1.4.2 Employer Recruitment - Partner with human resource groups and associations to promote hiring of individuals in target population. |  | 2021-07-01
1 | 1.4.3 Partner with Existing Efforts - partner with the Commission on Services for People with Disabilities and other advocacy group to promote and encourage recruitment and hiring of target population. |  | 2021-07-01
1 | 1.4.4 Outreach and Educate - outreach to NV businesses to introduce communication access options. |  | 2021-07-01
Activity Update
2019-11-13 | Workgroup established - Laura Fink and Eli Schwartz
2020-01-10 | First subcommittee meeting completed

## Resource
Goal # | Objective- Strategy | Member Assigned | Due Date | Completed
3 | 3.1.1 Develop Resource Guide - develop and disseminate an up to date guide | Cheyenne | 2020-05-13
4 | 4.1.2 Support Training Efforts - partner with community service providers to offer training and coaching to parents. |  | 2020-05-13
4 | 4.1.1 Advocate for Enhanced Services - work with state agencies and nonprofit organizations to support additional resource allocations for family support services. |  | 2020-07-08
Activity Update
2019-11-13 | Workgroup Established - Cheyenne Pasquale, Eli Schwartz
2020-01-16 | Website on hold pending ADSD leadership decisions

## Director
Goal # | Objective- Strategy | Member Assigned | Due Date | Completed
2 | 2.1.1 Advocate for Expanded ASL Classes - research options for expanding ASL classes throughout the state |  | 2020-03-19
1 | 1.2.3 Implement Plan to provide outreach and training to existing mental health providers. |  | 2020-05-13
1 | 1.2.1 Explore existing efforts and options to increase the number of mental health providers and innovative service provision througout Nevada. |  | 2020-07-08
2 | 2.2.1 Coordinate Advocacy Efforts - identify other entitites in which transportation has been identified as an access issue and develop a shared agenda for action. |  | 2021-01-01
2 | 2.3.1 Advocate for Policy Change and training to be inclusive of the target population in emergency response systems. |  | 2021-07-01
3 | 3.2.1 Promote and Encourage Cultrural Awareness - host community social events |  | 2021-07-01
Activity Update
2020-01-15 | Interviews completed for paid director position.